## Checklist
iFresh
Business planning checklist
Using the strength, weakness, opportunity, and threat (SWOT) analysis framework, develop a checklist of the key activities that need to be performed when preparing a formal business plan in the table, below.
Activity | Owner | Completion date
Phase 1: Initial Development (3 months). |  | 2024-06-30
Design user interface and experience (UI/UX) | Front-End Developer, CDO | 2024-04-30
Develop core features: - Ingredient list management - Expiration date tracking - Recipe suggestion - Healthy ingredient recommendation | Back-End Developer, AI Engineer | 2024-05-30
Test and optimize app performance | CTO, Developers | 2024-06-20
Prepare marketing strategy and launch plan | CEO, CMO, CFO | 2024-06-30
Phase 2: User Acquisition (6 months) |  | 2024-12-30
Increase online and offline marketing activities: - Facebook, Google Ads - SEO, SEM - Content marketing - Influencer marketing | CMO, CFO, CDO | 2024-12-30
Attend trade shows and events | CEO, CMO, CFO | 2024-12-30
Provide customer support | CMO | 2024-12-30
Phase 3: Expansion and Development (9 months) |  | 2025-12-30
Expand to new markets | CEO, CMO, CFO | 2025-12-30
Develop additional features: - Smart device integration - Nutritional data analysis - Ingredient shopping service | CTO, Developers | 2025-03-30
Collect data and analyze user behavior | CMO, CTO | 2025-08-30
Find new revenue streams | CEO, CMO, CTO | 2025-11-30
Phase 4: Maintenance and Sustainable Development (Future) | All Teams | Future
Continuously update and improve features |  | Future
Provide excellent customer service |  | Future
Monitor and evaluate performance |  | Future
Research and develop new features |  | Future